Piano Keys

Production Readiness Plan

12-Week Roadmap to Launch

Document Date: December 15, 2025

Version 1.0

Making Piano Keys Production-Ready and User-Centered

## Executive Summary

Current State: ~30% production ready

Well-architected AI-powered multi-genre piano transcription platform

CRITICAL security vulnerabilities: bypassed authentication, hardcoded secrets

Testing coverage gaps: 12-15% (need 80%)

Missing production infrastructure: SQLite (need PostgreSQL), local files (need S3)

Limited UX: no onboarding, minimal accessibility, dark mode only

Target State: 100% production ready in 12 weeks

Zero security vulnerabilities

80%+ test coverage with comprehensive E2E tests

Production-grade infrastructure (PostgreSQL, S3/MinIO, Redis caching)

User-centered design (onboarding, WCAG AA accessibility, contextual help)

Full CI/CD pipeline with monitoring and observability

Timeline: 12 weeks (1-2 engineers) Budget: ~$300/month infrastructure cost Strategy: Security-first, incremental deployment, no breaking changes

## 6-Phase Roadmap

### Phase 1: Security & Foundation (Weeks 1-2) - CRITICAL BLOCKERS

Goal: Eliminate critical security vulnerabilities

Week 1: Critical Security Fixes

Fix authentication bypass in `/backend/app/api/deps.py` (lines 30-48)

Replace hardcoded secret key in `/backend/app/core/security.py` (line 17)

Add rate limiting (slowapi) - 5 req/min auth, 10 req/hour uploads

Implement security headers middleware (HSTS, CSP, X-Frame-Options)

Add file upload security (MIME validation, virus scanning, random filenames)

Week 2: Foundation Infrastructure

Implement structured logging with correlation IDs (`structlog`)

Create global error handling middleware

Add React Error Boundaries to frontend

Set up secrets management and rotation

Remove 24 console.log statements from production code

Success Criteria: ✓ No authentication bypasses ✓ No hardcoded secrets ✓ Rate limiting active on all endpoints ✓ All errors logged with context

### Phase 2: Infrastructure Migration (Weeks 3-4)

Goal: Migrate to production-grade database and storage

Week 3: PostgreSQL Migration

Set up PostgreSQL 15+ with connection pooling

Configure Alembic migrations

Migrate SQLAlchemy from SQLite to PostgreSQL

Add database indexes for performance

Implement Redis caching layer (60%+ hit rate target)

Week 4: File Storage Migration

Set up MinIO (self-hosted S3)

Create storage abstraction layer (`storage_service.py`)

Migrate file handling to S3 with presigned URLs

Implement CDN-friendly headers

Test horizontal scaling with 2+ instances

Success Criteria: ✓ PostgreSQL migration complete (0 data loss) ✓ Redis cache hit rate > 60% ✓ All files in S3/MinIO ✓ Application stateless and scalable

### Phase 3: Testing & Quality (Weeks 5-7)

Goal: Achieve 80% test coverage and code quality standards

Week 5: Backend Testing

Configure pytest infrastructure with fixtures

Write 215+ backend tests (services, API routes, database)

Target: 80% backend coverage

Week 6: Frontend Testing

Set up Vitest + React Testing Library + MSW

Write 150+ frontend tests (components, routes, hooks)

Target: 80% frontend coverage

Week 7: E2E Tests & Code Quality

Write 20+ Playwright E2E tests for critical user journeys

Configure Ruff (backend) + ESLint/Prettier (frontend)

Set up mypy for type checking

Add pre-commit hooks for automated quality checks

Success Criteria: ✓ Backend coverage > 80% ✓ Frontend coverage > 80% ✓ 20+ E2E tests passing ✓ 0 linting/type errors

### Phase 4: User Experience & Accessibility (Weeks 8-9)

Goal: Make application user-centered with WCAG AA compliance

Week 8: Onboarding & User Accounts

Create authentication UI (login, signup, profile)

Build onboarding wizard (skill level, genre preferences, goals)

Implement help system and keyboard shortcuts modal

Add user preferences with cross-device sync

Make light/dark mode functional

Week 9: Accessibility & Notifications

Accessibility audit with axe-core

Add ARIA labels, keyboard navigation, screen reader support

Fix color contrast issues

Implement notification system (job completion, practice reminders)

Create accessible toast components

Success Criteria: ✓ WCAG AA compliance 100% ✓ Onboarding completion rate > 80% ✓ All features keyboard accessible ✓ Screen reader tested

### Phase 5: CI/CD & Monitoring (Weeks 10-11)

Goal: Automated deployment pipeline and full observability

Week 10: CI/CD Pipeline

Create GitHub Actions workflows (lint, test, security scan)

Build deployment automation (staging, production)

Implement blue-green deployment strategy

Set up staging environment

Create rollback procedures

Week 11: Monitoring & Observability

Implement Prometheus `/metrics` endpoint

Configure Grafana dashboards

Integrate Sentry for error tracking

Add APM for performance monitoring

Create operational runbooks

Success Criteria: ✓ CI pipeline runtime < 15 minutes ✓ Deployment time < 5 minutes ✓ Monitoring dashboards live ✓ Error tracking active

### Phase 6: Production Hardening (Week 12)

Goal: Final security audit, load testing, and launch preparation

Monday-Tuesday: Security Audit

Run OWASP ZAP automated scan

Check OWASP Top 10 vulnerabilities

Fix identified issues

Document security policy

Wednesday: Load Testing

Test with 100+ concurrent users (Locust/k6)

Optimize bottlenecks

Set performance baselines (API p95 < 200ms, FCP < 1.5s)

Thursday: Disaster Recovery

Implement automated backups

Test restoration procedures

Document recovery process (RTO < 1 hour)

Friday: Launch Checklist

Complete pre-launch checklist

Verify all tests passing

Configure SSL/TLS

Prepare post-launch monitoring

GO LIVE 🚀

Success Criteria: ✓ 0 critical vulnerabilities ✓ Handles 100+ concurrent users ✓ Backup/restore tested ✓ Launch checklist 100% complete

## Critical Files to Modify

### HIGHEST PRIORITY (Week 1)

**`/backend/app/api/deps.py`** - Remove authentication bypass (lines 30-48)

**`/backend/app/core/security.py`** - Replace hardcoded SECRET_KEY (line 17)

**`/backend/app/core/config.py`** - Add environment variable validation

**`/backend/app/main.py`** - Add middleware (rate limiting, security headers, error handling)

### HIGH PRIORITY (Weeks 2-4)

**`/backend/app/database/session.py`** - Migrate to PostgreSQL

**`/backend/.env.example`** - Document all environment variables

**`/frontend/src/routes/__root.tsx`** - Add Error Boundary

**`/backend/app/services/storage_service.py`** - Create S3 abstraction (NEW FILE)

### MEDIUM PRIORITY (Weeks 5-9)

**`/backend/tests/conftest.py`** - Test infrastructure

**`/frontend/src/test/utils.tsx`** - Frontend test utilities

**`/frontend/src/components/Piano.tsx`** - Accessibility improvements

**`/frontend/src/components/onboarding/OnboardingWizard.tsx`** - Onboarding flow (NEW FILE)

## Risk Mitigation & Rollback

### Database Migration (Week 3)

**Risk**: Data loss

**Mitigation**: Backup SQLite, test on copy, migrate during low-traffic window

**Rollback**: Revert to SQLite backup, RTO < 1 hour

### Authentication Changes (Week 1)

**Risk**: Locking out users

**Mitigation**: Create admin bypass token, test with multiple users, deploy during low-traffic

**Rollback**: Redeploy previous version, RTO < 5 minutes

### File Storage Migration (Week 4)

**Risk**: File access broken

**Mitigation**: Dual-write to local + S3, verify integrity, keep local copies 7 days

**Rollback**: Revert to local filesystem, RTO < 30 minutes

## Success Metrics

### Security

☐ 0 authentication bypasses

☐ 0 hardcoded secrets

☐ Rate limiting on 100% endpoints

☐ 0 critical vulnerabilities (OWASP scan)

### Testing

☐ Backend coverage > 80%

☐ Frontend coverage > 80%

☐ 20+ E2E tests passing

☐ 0 linting/type errors

### Infrastructure

☐ PostgreSQL migration (0 data loss)

☐ Redis cache hit rate > 60%

☐ All files in S3

☐ App runs with 2+ instances

### User Experience

☐ WCAG AA compliance 100%

☐ Onboarding completion > 80%

☐ Light/dark mode functional

☐ 100% keyboard navigation

### Performance

☐ API response p95 < 200ms

☐ Frontend FCP < 1.5s

☐ Handles 100+ concurrent users

☐ Uptime > 99.9%

## Resource Requirements

### Infrastructure Costs

**Staging**: $80/month (VPS, PostgreSQL, Redis, MinIO)

**Production**: $180/month (2x app servers, larger database, storage)

**Tools**: $40/month (Sentry, email service)

**Total**: ~$300/month

### Team

**Minimum**: 1 full-stack engineer (12 weeks full-time)

**Optimal**: 1 backend + 1 frontend engineer (8 weeks with parallel work)

## Critical Path Dependencies

**Phase 1 MUST complete first** - All other work blocked on security fixes

**Phase 2 depends on Phase 1** - Database/storage require secure config

**Phase 3 can run parallel to Phase 2** (after Week 2) - Testing independent of infrastructure

**Phase 4 depends on Weeks 1-2 of Phase 2** - User accounts need PostgreSQL

**Phase 5 depends on Phase 3** - CI/CD requires tests

**Phase 6 depends on all phases** - Cannot launch without security, testing, infrastructure

## Next Steps

When ready to execute:

**Start with Week 1, Day 1** - Fix authentication bypass in `deps.py`

**Create feature branch** - `feature/production-readiness-phase-1`

**Work incrementally** - Small PRs, frequent testing

**Track progress** - Use todo list for each week's tasks

**Test rollback procedures** - Before each major change

Key Principle: Security first, test everything, deploy incrementally, monitor closely.

## Party Mode Team Assessment

🧙 BMad Master's Recommendation: This plan prioritizes the unsexy but critical work - security hardening, comprehensive testing, and production infrastructure. The modular phase structure allows flexibility while maintaining clear dependencies. The 12-week timeline is achievable with 1-2 dedicated engineers.

Success requires discipline: Don't skip Phase 1 (security) to jump to "more interesting" UX work. The foundation must be solid before building up.